## gantt
PROJECT TITLE | rools
Réalisateur | Réalise la tâche et est responsable de son achèvement
Approbateur | Approuve l'achèvement d'une tâche. Seulement 1 par tâche.
Consultant | Conseille, intervient avant une descision ou une action.
Informé | Doit être informé après une décision ou une action.
Chaque options correspond a la creation de fonctionnalité (compatible linux et windows sauf dirscope), la mise a jour de l’argument parser (composant global), l’uniformisation des outputs success (txt, json, yaml, csv, hex et bin) et error (gestion fine multi OS), un fichier de test et un code clean selon le contrib.md
TASK | TASK | LB | DV | QD | DURATION | DEPENDANCE | LIMIT DATE | JAN | [30 empty] | FEB | [27 empty] | MAR | [30 empty] | APR | [29 empty] | MAY | [30 empty] | JUN
ID | TITLE | [6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Gestion | bar: WEEK 1 1; WEEK 4 28 to WEEK 5 30; WEEK 8 22 to WEEK 26 30
1.1 | Arbitrage du sujet |  |  |  | 7d | - | S2 | bar: WEEK 1 1
1.2 | Cahier des charges (fonctionnelle) |  |  |  | 5d | 1.1 | S3 | bar: WEEK 1 2 to WEEK 1 6
1.3 | Organisation de la gestion du projet |  |  |  | 1d | 1.2 | S3 | bar: WEEK 1 7
1.4 | Annexes (dépôt de code, canal de communications) |  |  |  | 1d | 1.1 | S3 | bar: WEEK 1 2
1.5 | Run un projet cargo, crée un main, un pre-prod et une branch dev par tools |  |  |  | 1d | 1.1 | S3 | bar: WEEK 1 2
1.6 | Cahier des charges (organisationnelle) |  |  |  | 1d | 1.3 | S3 | bar: WEEK 2 8
1.7 | Cahier des charges (technique) -> donc livrable final |  |  |  | 3d | * | S6 | bar: WEEK 19 8 to WEEK 19 10
2 | Global | bar: WEEK 4 28 to WEEK 5 30; WEEK 8 22 to WEEK 26 30
2.1 | options: --timeout |  |  |  | 3d | 1.5 | S3 | bar: WEEK 2 9 to WEEK 2 11
2.2 | options: --export |  |  |  | 3d | 1.5 | S5 | bar: WEEK 18 30 to WEEK 18 2
2.3 | options: --zip |  |  |  | 3d | 1.5 | S5 | bar: WEEK 18 3 to WEEK 18 5
2.4 | Merge pre-prod to main |  |  |  | 2d | * | S5 | bar: WEEK 18 6 to WEEK 19 7
3 | DirScope | bar: WEEK 4 28 to WEEK 5 30; WEEK 8 22 to WEEK 26 30
3.1 | options: --ldap-only |  |  |  | 3d | 2.1 | S5 | bar: WEEK 11 13 to WEEK 11 15
3.2 | options: --enabled |  |  |  | 3d | 2.1 | S5 | bar: WEEK 11 16 to WEEK 11 18
3.3 | options: --disabled |  |  |  | 3d | 2.1 | S5 | bar: WEEK 11 16 to WEEK 11 18
3.4 | options: --locked |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 19 to WEEK 12 21
3.5 | options: --expired |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 19 to WEEK 12 21
3.6 | options: --spn |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 22 to WEEK 12 24
3.7 | options: --asrep |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 22 to WEEK 12 24
3.8 | options: --kerberostable |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 25 to WEEK 13 27
3.9 | options: --des |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 25 to WEEK 13 27
3.10 | options: --password-never-expire |  |  |  | 3d | 2.1 | S5 | bar: WEEK 12 25 to WEEK 13 27
3.11 | options: --members |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 28 to WEEK 13 30
3.12 | options: --privileged |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 28 to WEEK 13 30
3.13 | options: --nested |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 28 to WEEK 13 30
3.14 | options: --unconstrained |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 31 to WEEK 14 2
3.15 | options: --constrained |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 31 to WEEK 14 2
3.16 | options: --ressource-based |  |  |  | 3d | 2.1 | S5 | bar: WEEK 13 31 to WEEK 14 2
3.17 | options: --spn-only |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 3 to WEEK 14 5
3.18 | options: --external |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 3 to WEEK 14 5
3.19 | options: --forest |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 3 to WEEK 14 5
3.20 | options: --direction |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 6 to WEEK 14 8
3.21 | options: --sid-filtering |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 6 to WEEK 14 8
3.22 | options: --object |  |  |  | 3d | 2.1 | S5 | bar: WEEK 14 6 to WEEK 14 8
3.23 | options: --privileged-only |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 9 to WEEK 15 11
3.24 | options: --effective-rights |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 9 to WEEK 15 11
3.25 | options: --help |  |  |  | 3d | 3.* | S5 | bar: WEEK 15 12 to WEEK 15 14
3.26 | Merge pre-prod |  |  |  | 2d | 3.25 | S5 | bar: WEEK 15 15 to WEEK 16 17
3.27 | Rédiger doc technique |  |  |  | 2d | 3.26 | S5 | bar: WEEK 16 18 to WEEK 16 20
4 | MalScan | bar: WEEK 4 28 to WEEK 5 30; WEEK 8 22 to WEEK 26 30
4.1 | options: --entropy |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 9 to WEEK 15 11
4.2 | options: --upx |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 12 to WEEK 15 14
4.3 | options: --yara |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 12 to WEEK 15 14
4.4 | options: --metadata |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 15 to WEEK 16 17
4.5 | options: --deep |  |  |  | 3d | 2.1 | S5 | bar: WEEK 15 15 to WEEK 16 17
4.6 | options: --recursive |  |  |  | 3d | 2.1 | S5 | bar: WEEK 16 18 to WEEK 16 20
4.7 | options: --flags |  |  |  | 3d | 2.1 | S5 | bar: WEEK 16 18 to WEEK 16 20
4.8 | options: --help |  |  |  | 3d | 4.* | S5 | bar: WEEK 16 21 to WEEK 17 23
4.9 | Merge pre-prod |  |  |  | 2d | 4.8 | S5 | bar: WEEK 17 24 to WEEK 17 26
4.10 | Rédiger doc technique |  |  |  | 2d | 4.9 | S5 | bar: WEEK 17 27 to WEEK 17 29
5 | MemTrace | bar: WEEK 4 28 to WEEK 5 30; WEEK 8 22 to WEEK 26 30
5.1 | options: --patern |  |  |  | 3d | 2.1 | S4 | bar: WEEK 5 30 to WEEK 5 1
5.2 | options: --signature |  |  |  | 3d | 2.1 | S4 | bar: WEEK 5 30 to WEEK 5 1
5.3 | options: --range |  |  |  | 3d | 2.1 | S4 | bar: WEEK 5 2 to WEEK 5 4
5.4 | options: --fast |  |  |  | 3d | 2.1 | S4 | bar: WEEK 5 2 to WEEK 5 4
5.5 | options: --auto |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 5 to WEEK 6 7
5.6 | options: --help |  |  |  | 3d | 5.* | S4 | bar: WEEK 6 8 to WEEK 6 10
5.7 | Merge pre-prod |  |  |  | 2d | 5.6 | S4 | bar: WEEK 6 11 to WEEK 7 13
5.8 | Rédiger doc technique |  |  |  | 2d | 5.7 | S4 | bar: WEEK 7 14 to WEEK 7 16
6 | NetWatch
6.1 | options: --pcap |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 5 to WEEK 6 7
6.2 | options: --filter |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 8 to WEEK 6 10
6.3 | options: --verbose |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 11 to WEEK 7 13
6.4 | options: --outbound |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 11 to WEEK 7 13
6.5 | options: --frequency |  |  |  | 3d | 2.1 | S4 | bar: WEEK 7 14 to WEEK 7 16
6.6 | options: --new-service |  |  |  | 3d | 2.1 | S4 | bar: WEEK 7 14 to WEEK 7 16
6.7 | options: --dns-leak |  |  |  | 3d | 2.1 | S4 | bar: WEEK 7 17 to WEEK 8 19
6.8 | options: --udp |  |  |  | 3d | 2.1 | S4 | bar: WEEK 7 17 to WEEK 8 19
6.9 | options: --range |  |  |  | 3d | 2.1 | S4 | bar: WEEK 7 17 to WEEK 8 19
6.10 | options: --stealth |  |  |  | 3d | 2.1 | S4 | bar: WEEK 8 20 to WEEK 8 22
6.11 | options: --top |  |  |  | 3d | 2.1 | S4 | bar: WEEK 8 20 to WEEK 8 22
6.12 | options: --help |  |  |  | 3d | 6.* | S4 | bar: WEEK 8 23 to WEEK 8 25
6.13 | Merge pre-prod |  |  |  | 2d | 6.12 | S4 | bar: WEEK 9 26 to WEEK 9 28
6.14 | Rédiger doc technique |  |  |  | 2d | 6.13 | S4 | bar: WEEK 9 1 to WEEK 9 3
7 | SentryProc
7.1 | options: --pid |  |  |  | 3d | 2.1 | S3 | bar: WEEK 2 12 to WEEK 2 14
7.2 | options: --user |  |  |  | 3d | 2.1 | S3 | bar: WEEK 2 12 to WEEK 2 14
7.3 | options: --runing |  |  |  | 3d | 2.1 | S3 | bar: WEEK 2 12 to WEEK 2 14
7.4 | options: --sensitive |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 15 to WEEK 3 17
7.5 | options: --file-access |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 15 to WEEK 3 17
7.6 | options: --unsigned |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 15 to WEEK 3 17
7.7 | options: --hidden |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 18 to WEEK 3 20
7.8 | options: --high-cpu |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 18 to WEEK 3 20
7.9 | options: --network |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 18 to WEEK 3 20
7.10 | options: --help |  |  |  | 3d | 7.* | S3 | bar: WEEK 3 21 to WEEK 4 23
7.11 | Merge pre-prod |  |  |  | 2d | 7.10 | S3 | bar: WEEK 4 24 to WEEK 4 26
7.12 | Rédiger doc technique |  |  |  | 2d | 7.11 | S3 | bar: WEEK 4 27 to WEEK 5 29
8 | SkyWave
8.1 | options: --chanel |  |  |  | 3d | 2.1 | S4 | bar: WEEK 6 8 to WEEK 6 10
8.2 | options: --ssid |  |  |  | 3d | 2.1 | S4 | bar: WEEK 8 20 to WEEK 8 22
8.3 | options: --bssid |  |  |  | 3d | 2.1 | S4 | bar: WEEK 8 23 to WEEK 8 25
8.4 | options: --hidden |  |  |  | 3d | 2.1 | S4 | bar: WEEK 8 23 to WEEK 8 25
8.5 | options: --signal |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 26 to WEEK 9 28
8.6 | options: --wep |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 26 to WEEK 9 28
8.7 | options: --wpa |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 1 to WEEK 9 3
8.8 | options: --wpa3 |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 1 to WEEK 9 3
8.9 | options: --default-pass |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 4 to WEEK 10 6
8.10 | options: --pmkid |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 4 to WEEK 10 6
8.11 | options: --ap |  |  |  | 3d | 2.1 | S4 | bar: WEEK 9 4 to WEEK 10 6
8.12 | options: --ip-only |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 7 to WEEK 10 9
8.13 | options: --mac-only |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 7 to WEEK 10 9
8.14 | options: --ssid (cmd: test) |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 7 to WEEK 10 9
8.15 | options: --bssid (cmd: test) |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 10 to WEEK 11 12
8.16 | options: --deauth |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 10 to WEEK 11 12
8.17 | options: --evil-twin |  |  |  | 3d | 2.1 | S4 | bar: WEEK 10 10 to WEEK 11 12
8.18 | options: --handshake-capture |  |  |  | 3d | 2.1 | S4 | bar: WEEK 11 13 to WEEK 11 15
8.19 | options: --wps |  |  |  | 3d | 2.1 | S4 | bar: WEEK 11 13 to WEEK 11 15
8.20 | options: --help |  |  |  | 3d | 8.* | S4 | bar: WEEK 11 16 to WEEK 11 18
8.21 | Merge pre-prod |  |  |  | 2d | 8.20 | S4 | bar: WEEK 12 19 to WEEK 12 21
8.22 | Rédiger doc technique |  |  |  | 2d | 8.21 | S4 | bar: WEEK 12 22 to WEEK 12 24
9 | SysViz
9.1 | options: --pid |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 21 to WEEK 4 23
9.2 | options: --name |  |  |  | 3d | 2.1 | S3 | bar: WEEK 3 21 to WEEK 4 23
9.3 | options: --stats |  |  |  | 3d | 2.1 | S3 | bar: WEEK 4 24 to WEEK 4 26
9.4 | options: --latency |  |  |  | 3d | 2.1 | S3 | bar: WEEK 4 24 to WEEK 4 26
9.5 | options: --top |  |  |  | 3d | 2.1 | S3 | bar: WEEK 4 27 to WEEK 5 29
9.6 | options: --alert |  |  |  | 3d | 2.1 | S3 | bar: WEEK 4 27 to WEEK 5 29
9.7 | options: --help |  |  |  | 3d | 9.* | S3 | bar: WEEK 5 30 to WEEK 5 1
9.8 | Merge pre-prod |  |  |  | 2d | 9.7 | S3 | bar: WEEK 5 2 to WEEK 5 4
9.9 | Rédiger doc technique |  |  |  | 2d | 9.8 | S3 | bar: WEEK 6 5 to WEEK 6 7
10 | WebScout
10.1 | options: --sql |  |  |  | 3d | 2.1 | S5 | bar: WEEK 16 21 to WEEK 17 23
10.2 | options: --xss |  |  |  | 3d | 2.1 | S5 | bar: WEEK 16 21 to WEEK 17 23
10.3 | options: --csrf |  |  |  | 3d | 2.1 | S5 | bar: WEEK 17 24 to WEEK 17 26
10.4 | options: --dirlist |  |  |  | 3d | 2.1 | S5 | bar: WEEK 17 24 to WEEK 17 26
10.5 | options: --fuzz |  |  |  | 3d | 2.1 | S5 | bar: WEEK 17 27 to WEEK 17 29
10.6 | options: --depth |  |  |  | 3d | 2.1 | S5 | bar: WEEK 17 27 to WEEK 17 29
10.7 | options: --forms |  |  |  | 3d | 2.1 | S5 | bar: WEEK 18 30 to WEEK 18 2
10.8 | options: --links |  |  |  | 3d | 2.1 | S5 | bar: WEEK 18 30 to WEEK 18 2
10.9 | options: --help |  |  |  | 3d | 10.* | S5 | bar: WEEK 18 3 to WEEK 18 5
10.10 | Merge pre-prod |  |  |  | 2d | 10.9 | S5 | bar: WEEK 18 6 to WEEK 19 8
10.11 | Rédiger doc technique |  |  |  | 2d | 10.10 | S5 | bar: WEEK 19 9 to WEEK 19 11